AGROCONNECT CAMEROON

Software Development Project Documentation

Release & Sprint Plan  |  Test Plan & Test Cases  |  Risk Management

Version 1.0

June 2026

Repository: github.com/Ghost590-beep/AgroConnect-Cameroon

Tech Stack: React + TypeScript | Node.js + Express | MySQL | JWT | Vercel + Render + Railway

Confidential — Internal Project Document

# Section 1: Release & Sprint Plan

This section outlines the project delivery schedule for AgroConnect Cameroon, structured across six releases and thirteen sprints. The plan follows Agile Scrum methodology with 2-week sprint cycles (Sprints 1–10) and 1-week finalization sprints (Sprints 11–13).

## 1.1 Sprint Schedule Overview

The table below maps each release to its constituent sprints, the functional requirements covered, and the planned delivery period.

| Release | Sprint | ID of User Stories | Period |
| --- | --- | --- | --- |
| Release 1: Core Setup | Sprint 1 | FR1, FR2 | Feb 3 – Feb 16 |
|  | Sprint 2 | FR3, FR4 | Feb 17 – Mar 2 |
| Release 2: Transactions | Sprint 3 | FR5 | Mar 3 – Mar 16 |
|  | Sprint 4 | FR6 | Mar 17 – Mar 30 |
| Release 3: Communication | Sprint 5 | FR7 | Mar 31 – Apr 13 |
|  | Sprint 6 | FR8 | Apr 14 – Apr 27 |
| Release 4: Skills & Training | Sprint 7 | FR9 | Apr 28 – May 11 |
|  | Sprint 8 | FR10 | May 12 – May 25 |
| Release 5: Employment | Sprint 9 | FR11 | May 26 – Jun 8 |
|  | Sprint 10 | FR12 | Jun 9 – Jun 22 |
| Release 6: Finalization (1-week) | Sprint 11 | Integration & Testing | Jun 23 – Jun 29 |
|  | Sprint 12 | Deployment & Review | Jun 30 – Jul 6 |
|  | Sprint 13 | Retrospective & Documentation | Jul 7 – Jul 13 |

## 1.2 Release Descriptions

Release 1: Core Setup (Sprints 1–2)

Establishes the project foundation: user authentication (registration and login with JWT), role-based access control, and the basic platform structure. FR1 covers multi-role registration (Farmer, Buyer, Service Provider); FR2 covers login, session management, and dashboard access.

Release 2: Transactions (Sprints 3–4)

Implements the marketplace engine. FR5 enables product listing creation and browsing; FR6 introduces cart management for buyers, including add, remove, and quantity update functionality with XAF pricing.

Release 3: Communication (Sprints 5–6)

Adds real-time communication capabilities. FR7 covers the direct messaging module between any two platform users; FR8 implements the notification system for order events, messages, and status updates.

Release 4: Skills & Training (Sprints 7–8)

Introduces trust and engagement features. FR9 enables buyers to submit product reviews and ratings after verified purchases; FR10 provides the favourites/wishlist feature for buyers to bookmark preferred products.

Release 5: Employment (Sprints 9–10)

Completes the core commerce loop. FR11 manages delivery records, status tracking, and logistics provider coordination; FR12 implements escrow-based payment holding and release tied to delivery confirmation, with support for MTN MoMo and Orange Money in XAF.

Release 6: Finalization (Sprints 11–13)

Dedicated finalization phase using shortened 1-week sprints. Sprint 11 focuses on full integration testing and bug resolution across all modules. Sprint 12 handles production deployment to Vercel, Render, and Railway with CI/CD pipeline validation. Sprint 13 conducts the project retrospective and completes all technical documentation.

# Section 2: Test Plan & Test Cases

This section defines the complete testing strategy for AgroConnect Cameroon, covering all 12 functional requirements (FR1–FR12). Testing is structured into four tiers: acceptance criteria, unit/functional test cases, integration tests, and regression tests. The backend testing framework uses Jest with Supertest; API exploration uses Swagger UI at /api-docs.

## 2.1 Testing Scope & Strategy

| Testing Type | Approach & Tools |
| --- | --- |
| Unit / Functional | Jest + Supertest on Express routes. Validates individual endpoints for correct HTTP response codes, payload structure, and validation behavior. |
| Integration | End-to-end multi-step flows tested via Supertest and manual Swagger testing. Covers full user journeys across modules. |
| Regression | Automated re-execution of the full Jest suite on every pull request via GitHub Actions CI. Triggered by any code change. |
| Acceptance | Verified against the functional requirements defined in the backlog. Validated during Sprint Review with Product Owner sign-off. |
| Security | OWASP ZAP API scans, JWT token validation tests, CORS header inspection. Rate limiting deferred to post-release. |
| Performance | Load testing with k6 on critical endpoints (/api/products, /api/orders) targeting <500ms response under 100 concurrent users. |

## 2.2 Acceptance Criteria by Feature

Acceptance criteria define the minimum observable behaviour required for each functional requirement to be considered complete and accepted by the Product Owner.

| FR | Feature | Acceptance Criteria |
| --- | --- | --- |
| FR1 | User Registration | System accepts valid farmer, buyer, and service provider registrations; rejects duplicates and invalid inputs; returns JWT on success. |
| FR2 | User Login | Valid credentials return JWT; wrong credentials return 401; JWT must expire after defined period. |
| FR3 | Product Listing | Authenticated sellers can create listings with title, price (XAF), category, and image; listings appear in marketplace. |
| FR4 | Product Detail | Any user can retrieve full product details including seller info, price, category, and images by product ID. |
| FR5 | Order Placement | Authenticated buyers can place orders; order is persisted with status 'pending'; sellers can view incoming orders. |
| FR6 | Cart Management | Buyers can add/remove products from cart; cart persists across sessions; quantities update correctly. |
| FR7 | Messaging | Users can send and receive messages; conversation history is retrievable; messages are not accessible by third parties. |
| FR8 | Notifications | System sends notifications on order events, messages, and status updates; users can retrieve their notification list. |
| FR9 | Reviews & Ratings | Buyers can submit one review per product after purchase; ratings are aggregated and displayed on product pages. |
| FR10 | Favourites | Users can favourite/unfavourite products; favourite list is persisted and retrievable per user. |
| FR11 | Delivery Management | Delivery records are created per order; status can be updated to reflect transit and delivery milestones. |
| FR12 | Escrow & Payments | Escrow holds funds on order creation; funds are released upon delivery confirmation; payment providers list supported mobile money options (XAF). |

## 2.3 Test Cases (TC-001 to TC-028)

The following test cases cover authentication, product management, transactions, communication, engagement, and payment features. Status reflects current Sprint progress.

| TC ID | FR | Module | Test Case | Type | Steps | Expected Result | Priority | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TC-001 | FR1 | Auth | Register with valid farmer credentials | Functional | POST /api/auth/register with full payload | 201 Created, JWT token returned | High | Pass |
| TC-002 | FR1 | Auth | Register with duplicate email | Negative | POST /api/auth/register with existing email | 409 Conflict, error message | High | Pass |
| TC-003 | FR1 | Auth | Register with missing required fields | Validation | POST /api/auth/register without password | 400 Bad Request | Medium | Pass |
| TC-004 | FR2 | Auth | Login with valid credentials | Functional | POST /api/auth/login with correct email/password | 200 OK, JWT returned | High | Pass |
| TC-005 | FR2 | Auth | Login with wrong password | Negative | POST /api/auth/login with incorrect password | 401 Unauthorized | High | Pass |
| TC-006 | FR2 | Auth | Access protected route without token | Security | GET /api/auth/:id without Authorization header | 401 Unauthorized | High | Pass |
| TC-007 | FR3 | Products | Create product with valid data | Functional | POST /api/products with JWT, valid body | 201 Created, product object | High | Pass |
| TC-008 | FR3 | Products | Create product without auth | Security | POST /api/products without token | 401 Unauthorized | High | Pass |
| TC-009 | FR3 | Products | List all products | Functional | GET /api/products | 200 OK, products array | Medium | Pass |
| TC-010 | FR4 | Products | Get product by valid ID | Functional | GET /api/products/:id with existing ID | 200 OK, product object | Medium | Pass |
| TC-011 | FR4 | Products | Get product by invalid ID | Negative | GET /api/products/99999 | 404 Not Found | Medium | Pass |
| TC-012 | FR5 | Orders | Place order as buyer | Functional | POST /api/orders with valid product ID and buyer JWT | 201 Created, order object | High | Pending |
| TC-013 | FR5 | Orders | Get order by ID | Functional | GET /api/orders/:id with auth | 200 OK, order details | High | Pending |
| TC-014 | FR6 | Cart | Add item to cart | Functional | POST /api/cart with product ID and qty | 200 OK, updated cart | High | Pending |
| TC-015 | FR6 | Cart | Retrieve cart contents | Functional | GET /api/cart with auth | 200 OK, cart items | Medium | Pending |
| TC-016 | FR7 | Messages | Send message between users | Functional | POST /api/messages with senderId, receiverId, body | 201 Created, message object | High | Pending |
| TC-017 | FR7 | Messages | Retrieve conversation history | Functional | GET /api/messages/conversation/:userAId/:userBId | 200 OK, message list | High | Pending |
| TC-018 | FR8 | Notifications | Send notification to user | Functional | POST /api/notifications/:userId/send with payload | 200 OK, notification sent | Medium | Pending |
| TC-019 | FR8 | Notifications | Get all notifications for user | Functional | GET /api/notifications/:userId | 200 OK, notifications array | Medium | Pending |
| TC-020 | FR9 | Reviews | Submit product review | Functional | POST /api/reviews with rating and comment | 201 Created, review object | Medium | Pending |
| TC-021 | FR9 | Reviews | Get reviews for a product | Functional | GET /api/reviews/product/:productId | 200 OK, reviews list | Medium | Pending |
| TC-022 | FR10 | Favorites | Add product to favourites | Functional | POST /api/favorites with productId | 200 OK, favourite added | Low | Pending |
| TC-023 | FR10 | Favorites | List user's favourites | Functional | GET /api/favorites/user/:userId | 200 OK, favourite list | Low | Pending |
| TC-024 | FR11 | Delivery | Create delivery record | Functional | POST /api/deliveries with order ID | 201 Created, delivery record | High | Pending |
| TC-025 | FR11 | Delivery | Get delivery by ID | Functional | GET /api/deliveries/:id | 200 OK, delivery details | Medium | Pending |
| TC-026 | FR12 | Escrow | Create escrow for order | Functional | POST /api/escrows with order ID and amount | 201 Created, escrow object | High | Pending |
| TC-027 | FR12 | Escrow | Retrieve escrow by order ID | Functional | GET /api/escrows/:orderId | 200 OK, escrow details | High | Pending |
| TC-028 | FR12 | Payment | List payment providers | Functional | GET /api/payment-providers | 200 OK, providers list | Medium | Pending |

## 2.4 Integration Test Scenarios

Integration tests validate that multiple components work together correctly across complete user journeys. These are executed during Sprint 11 integration testing.

| ID | Scenario | Test Steps | Expected Outcome |
| --- | --- | --- | --- |
| INT-001 | Full Registration & Login Flow | Register → Login → Access protected route | End-to-end token flow works correctly |
| INT-002 | Product Create & Browse Flow | Login as Seller → POST product → GET /api/products → verify listing | Product appears in marketplace listing |
| INT-003 | Buyer Order Placement | Login as Buyer → Add to cart → POST /api/orders → GET order | Order created with correct status and buyer info |
| INT-004 | Messaging Between Users | UserA sends message to UserB → UserB fetches conversation | Message is persisted and retrievable |
| INT-005 | Escrow & Payment Flow | Place order → Create escrow → Verify escrow linked to order | Escrow amount matches order total in XAF |
| INT-006 | Delivery Tracking Integration | Create delivery for order → Update delivery status → Buyer retrieves status | Status updates visible to buyer in real time |
| INT-007 | Review After Purchase | Complete order → Submit review for product → Retrieve reviews | Review saved and linked to verified purchase |
| INT-008 | Notification on Order Event | Seller posts product → Buyer places order → Seller receives notification | Notification delivered to correct user |

## 2.5 Regression Test Plan

Regression tests are re-executed on every code merge to the main branch via GitHub Actions. Each test is mapped to the area of the codebase most likely to introduce regressions.

| ID | Area | Description | Trigger Condition |
| --- | --- | --- | --- |
| REG-001 | Authentication | Verify JWT middleware blocks unauthenticated access after any auth change | Any modification to auth middleware or route guards |
| REG-002 | Product API | Confirm product CRUD operations still function correctly | Schema or controller changes in products module |
| REG-003 | Order Processing | Validate order creation, retrieval, and status flow | Business logic changes in orders or escrow modules |
| REG-004 | User Profile | Ensure profile update (PUT /api/auth/:id/profile) saves and returns correct data | User model or profile route changes |
| REG-005 | Database Connectivity | Confirm all repository queries execute without error on schema changes | MySQL schema updates or migrations |
| REG-006 | CORS & Security Headers | Verify CORS policy correctly allows/blocks origins in production | Deployment config or server.js changes |
| REG-007 | File Uploads | Confirm Multer correctly handles image uploads within size limits | Any update to upload configuration |
| REG-008 | Swagger Docs | Ensure /api-docs route loads and reflects current route definitions | Any new route addition or modification |

## 2.6 Test Entry & Exit Criteria

Entry Criteria

• Feature branch merged to main and passing CI pipeline checks.

• Swagger UI reflects current route definitions for the sprint.

• Database seed data available and schema migration applied.

Exit Criteria

• All High-priority test cases pass with no open critical defects.

• Integration tests INT-001 to INT-008 pass without errors.

• Code coverage >= 70% across server/src modules (target 80% by Sprint 11).

• Product Owner has reviewed and signed off on the sprint demo.

# Section 3: Risk Management Document

This document identifies, categorizes, and provides mitigation strategies for all known risks associated with the AgroConnect Cameroon project. Risks are assessed across three dimensions: Likelihood, Impact, and Exposure (Likelihood × Impact). Risk owners are responsible for monitoring and executing mitigation actions.

## 3.1 Risk Assessment Framework

| Level | Likelihood | Impact | Exposure |
| --- | --- | --- | --- |
| Low | Unlikely (< 20% probability) | Minor disruption, easily absorbed | Low — monitor only |
| Medium | Possible (20–60%) | Noticeable delay or partial feature loss | Medium — active mitigation |
| High | Likely (> 60%) | Significant schedule or budget overrun | High — immediate action |
| Critical | Near-certain | Project failure or data breach | Critical — escalate immediately |

## 3.2 Risk Summary

| Category | Total Risks | High/Critical | Medium | Open |
| --- | --- | --- | --- | --- |
| Technical | 6 | 5 | 1 | 6 |
| Operational | 4 | 3 | 1 | 4 |
| Market | 4 | 2 | 2 | 4 |
| TOTAL | 14 | 10 | 4 | 14 |

## 3.3 Technical Risks

Technical risks arise from the chosen technology stack (Node.js, MySQL, React, Railway), integration points, and security vulnerabilities.

| Risk ID | Risk Title | Likelihood | Impact | Exposure | Mitigation Strategy | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RISK-T01 | Database Connectivity Failure | Medium | High | High | Implement connection pooling, retry logic, and health checks. Configure Railway alerts. Maintain a backup MySQL instance with automated failover. | Database/DevOps Engineer | Open |
| RISK-T02 | Payment Gateway Unavailability | Medium | High | High | Implement graceful fallback messaging, queue failed payment attempts, and integrate WireMock for development mocking. Monitor API uptime dashboards. | Backend Developer | Open |
| RISK-T03 | JWT Token Expiry and Security Exploit | Low | Critical | High | Use refresh token rotation, store JWT_SECRET in environment variables only, enable HTTPS in production, and audit token handling quarterly. | Backend Developer | Open |
| RISK-T04 | File Upload Exploitation | Medium | Medium | Medium | Validate file type (whitelist png, jpg, jpeg only), enforce file size limits (max 5MB), store uploads in isolated cloud storage (not /public), and run virus scanning. | Backend Developer | Open |
| RISK-T05 | Frontend-Backend Integration Failure | High | Medium | High | Define and document API contracts early using Swagger. Enforce CORS origin whitelist. Run integration tests (INT-001 to INT-008) before each release. | Full Stack Developers | Open |
| RISK-T06 | Deployment Pipeline Failure | Medium | High | High | Set up automated deployment tests in GitHub Actions. Maintain staging environment that mirrors production. Use blue-green deployment strategy. | DevOps Engineer | Open |

## 3.4 Operational Risks

Operational risks stem from team dynamics, process adherence, and project management practices within the 5-member Agile Scrum team.

| Risk ID | Risk Title | Likelihood | Impact | Exposure | Mitigation Strategy | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RISK-O01 | Team Member Unavailability | Medium | Medium | Medium | Cross-train team members on adjacent areas. Document all features and code thoroughly. Maintain shared codebase knowledge via weekly walkthroughs. | Scrum Master | Open |
| RISK-O02 | Scope Creep | High | High | High | Strict backlog management by Product Owner. All new feature requests go through sprint review before being scheduled. Use MoSCoW prioritization. | Product Owner | Open |
| RISK-O03 | Inadequate Testing Coverage | High | High | High | Expand Jest test suite to cover service layer and controller logic. Add Cypress end-to-end tests for frontend. Target 80%+ code coverage before Sprint 11. | All Developers | Open |
| RISK-O04 | Documentation Lag | High | Medium | Medium | Enforce documentation as part of the Definition of Done (DoD). Update Swagger JSDoc on every route file change. Schedule Sprint 13 dedicated to documentation. | Scrum Master / All | Open |

## 3.5 Market Risks

Market risks relate to the external environment, including infrastructure limitations in Cameroon, user adoption challenges, regulatory constraints, and competitive dynamics.

| Risk ID | Risk Title | Likelihood | Impact | Exposure | Mitigation Strategy | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| RISK-M01 | Low Internet Connectivity in Target Regions | High | High | High | Optimize frontend bundle size. Implement offline-first caching strategies. Consider SMS/USSD fallback for core order and notification flows in future releases. | Product Owner / Frontend | Open |
| RISK-M02 | Low User Adoption | Medium | High | High | Conduct user research and usability testing with Cameroonian farmers. Provide multilingual support (French/English). Create onboarding tutorials and tooltips. | Product Owner | Open |
| RISK-M03 | Currency and Payment Regulation Risk | Low | High | Medium | Consult with a local fintech legal advisor. Partner with licensed payment processors (e.g., CinetPay, PayDunya) that are already compliant with BEAC regulations. | Product Owner | Open |
| RISK-M04 | Competitive Platforms | Medium | Medium | Medium | Differentiate through escrow security, agricultural-specific categories (crops, livestock, equipment), and trust features like farmer verification and reviews. | Product Owner | Open |

## 3.6 Risk Monitoring & Review Schedule

| Review Point | Activities | Responsible Party |
| --- | --- | --- |
| Sprint Planning | Review new and updated risks before each sprint; adjust mitigation tasks in backlog | Scrum Master + Team |
| Sprint Review | Validate that mitigation actions for sprint-specific risks were executed | Scrum Master + PO |
| Retrospective | Assess whether any risks materialized and update risk register accordingly | Full Team |
| Release Gate (Sprint 11) | Full risk audit before production deployment; all Critical/High risks must have active mitigations | Product Owner |
| Post-Launch (Sprint 13) | Document lessons learned; archive risk register for future project phases | Scrum Master |

## 3.7 Contingency Plans

Database Failure Contingency

If Railway MySQL becomes unavailable: switch to read-only mode surfacing cached product data; notify users via banner; restore from automated backup (RPO: 24 hours, RTO: 4 hours).

Payment Gateway Outage Contingency

Queue all payment attempts locally using a persistent job queue. Surface a clear user-facing message in XAF: 'Payment processing temporarily unavailable. Your order is saved.' Re-attempt processing when gateway recovers.

Team Member Loss Contingency

If a backend developer is unavailable during a sprint: Scrum Master reassigns the most critical API tasks to the full-stack developer. Sprint scope is reduced by removing Medium/Low priority items. Carry-over tasks are added to the next sprint backlog.

Deployment Failure Contingency

Maintain a known-good release tag on GitHub. Vercel and Render support one-click rollback to previous deployment. If CI/CD pipeline fails, execute manual deployment from the last stable tag and investigate pipeline errors in Sprint 11 buffer time.